Event Timeline Template

Summary

An event operations timeline is the “playbook” of the entire event and is critical to keeping all stakeholders and team members on track. It is a chronological list of the tasks that need to be completed for your event.

Event operations timelines allow you to set deadlines and assign tasks. It is a master “to-do” list for your event. Once you create your timeline, share it and meet on a regular basis to ensure each item is completed on time.

Best Practices in Event Timelines

This sample timeline provides best practices in developing key milestone dates and more detail is necessary to add for your individual event.

It is important to:

- Include actual dates for your event in the timeline

- Assign all tasks to an individual/s

- Share the timeline with team members meet regularly to discuss progress, checking off items as they are completed.

- This is an important document—keep it updated and sharable

Customizable Timeline Template.xlsx

| Time | Task |
| --- | --- |
| 18 to 12 months out PLACE ACTUAL DATES HERE | Gather event stakeholders and outline event purpose, goals and objectives |
|  | Finalize event date/s with stakeholders |
|  | Select event type and develop event agenda / attendee experience—review with stakeholders |
|  | Create and finalize budget |
|  | Conduct site visits and contract venue |
|  | Begin sourcing event vendors (AV, décor, etc.) |
| 12 to 9 months out | Refine event design and secure speakers, entertainment |
|  | Contract event vendors |
|  | Short-list solutions for attendee registration/ticket sales |
|  | Develop sponsorship packages and create target sponsor list |
|  | Create event marketing plan and distribute to stakeholders for feedback |
| 9 to 6 months out | Select registration vendor and write registration policies and procedures |
|  | Begin monthly budget meetings with stakeholders |
|  | Launch event marketing plan (teasers, save the date) |
|  | Finalize all vendor contracts / make deposits as necessary |
|  | Sponsorship sales |
|  | Write event contingency plan / secure event insurance |
| 6 to 3 months out | Launch attendee registration and begin weekly registration updates to stakeholders |
|  | Execute event marketing plan and adjust if necessary |
|  | Refine and finalize event design and participant experience / conduct additional site visit if necessary |
|  | Finalize sponsorship sales (three months out) |
|  | Begin event volunteer recruitment or contract temporary labor if needed |
|  | Finalize stage and signage designs |
|  | Begin a list of host speakers/presenters and draft scripting talking points |
| 3 months to 1 month out | Select menus and finalize room sets based on anticipated attendance |
|  | Write Group Resume and Event Specifications and Orders for the venue and each vendor (2 months out) |
|  | Place all final orders—signage, merchandise, supplies |
|  | Write on-site work plan with individual assignments and responsibilities; develop any training documents if needed |
|  | Write Event Emergency Plan |
|  | Finalize all scripting for stage time, announcements, etc. |
|  | Write event evaluation survey and distribute to stakeholders |
| Month of the event | Conduct on-site meeting and event walk through with venue and necessary vendors |
|  | Conduct briefing calls with keynotes, panelists or other session speakers |
|  | Conduct briefing calls with all sponsors and send final on-site details in writing |
|  | Confirm entertainment details and requirements |
|  | Update and send Event Specifications or Orders if necessary |
|  | Ship items to venue if needed (no more than 2 weeks out) |
| Week of the event | Conduct a team meeting to review the on-site workplan |
|  | Confirm and communicate final food and beverage catering guarantees |
|  | Send a “What to Know Before You Go” communication to all registered attendees with key pieces of information for the event |
|  | Confirm all event supplies, shipments and signage have arrived |
|  | Hold pre-event (pre-con) meeting with venue to review Group Resume and Banquet Orders, correct as necessary |
|  | Conduct rehearsals as necessary |
| Post-Event 1 week to 30 days post event | Receive and review final invoices from venue and all vendors; make corrections as necessary |
|  | Run final registration reports |
|  | Send evaluation survey to attendees / evaluate results |
|  | Final budget reconciliation |
|  | Review event with sponsors for feedback |
|  | Send thank you letters to all presenters and those who supported your event |
|  | Conduct an internal review of venue and vendors |
|  | Pay final invoices |